## Risk Tracking Template
Risk Register Tracking Template for XXX Group
Date of last review: |  |  |  | (DD/MM/YYY)
ID | Category | Risk Level (appetite) | Description of Risk | Impact | Risk Response | Risk owner | Action owner | Likelihood Score | Impact Score | Overall Score | Notes
1 | Operational | Accepted | Volunteer skills - insufficient trained leaders | Inability to run one or more sections | Temporarily close section or ask for district support | Group Lead Volunteer | Group Lead Volunteer | 3 | 3 | 3 | Maintain ongoing review and training process with succession planning section by section
2 | Operational | Fix | Volunteer skills - insufficient trained and competent trustees | Unable to fulfil requirements of charities commission and POR | Recruit and train trustees. In extremis decision to close/merge group | Chair of trustees | Chair of trustees | 5 | 5 | 5 | Recruitment and training programme for new trustees and existing trustees to be immediately prioritised. Support to be sought from district and county teams
3 | Operational | Accepted | Quality and alignment of the programme insufficient | Poor experience for young people and leaders. Failure to recruit and retain. | Support and train sectional volunteers. | Group Lead Volunteer | Section Lead Volunteers | 2 | 3 | 2.5 | Programmes regularly reviewed by GLV. Programme planning and delivery is a core part of volunteer training
4 | Operational | Accepted | Child protection and vetting failure leading to safeguarding incident | Harm to young personor adult, major reputational damage | Full safeguarding response as required in POR | Group Lead Volunteer | Group Lead Volunteer | 1 | 5 | 3 | Compliance with yellow card part of group culture and reviewed regularly at section and board. All members trained and vetted as required
5 | Operational |  | Adult learning and development |  |  |  |  | 1 | 1 | 1
6 | Operational |  | Succession planning |  |  |  |  | 1 | 1 | 1
7 | Operational |  | Condition of property /buildings does not meet regulatory need
8 | Operational |  | Size of building insufficient for growth
9 | Operational
10 | Operational
11 | Governance | Fix | Trustee skill set not complete to allow board to fulfil role | Unable to fulfil requirements of charities commission and POR | Recruit and train trustees. In extremis decision to close/merge group | Chair of trustees | Chair of trustees | 2 | 3 | 2.5 | Recruitment and training programme for new trustees and existing trustees to be immediately prioritised. Support to be sought from district and county teams
12 | Governance | Accepted | Management information provided to trustees incorrect or insufficient | Unable to fulfil requirements of charities commission and POR. Poor or inaccurate deciision making | Review materials being used by board of trustees and agendas used against purpose of trustee baord | Chair of trustees | Chair of trustees and treasurer | 3 | 3 | 3 | Annual review to be carried out prior to AGM
13 | Governance | Accepted | Conflicts of interests | Failure to correctly allocate resources having negative impact on efficiency and effectiveness of running the group | If conflict is identified trustees action to be taken to ensure resources are appropriately allocated. | Chair of trustees | Chair of trustees | 4 | 3 | 3.5 | Compliance with POR on conflict of intrests. All trustees to declare any potential conflicts of interest in advance of agenda item and conflicts to be minuted
14 | Legal and regulatory | Accepted | Health and safety Law breach leading to accident or injury | Individual hurt, harm or alarm. Reputational damage. Adverse press. | Respond according to incident as required under POR and legal requirements | Chair of trustees | Safety Lead trustee | 1 | 5 | 3 | Health and saety policy in place and compliance audited. Health and safety a key part of group culture and reviewed in Baord and sectional meetings
15 | Legal and regulatory |  | failure to comly with POR & the Charity Commission requirements |  |  |  |  | 1 | 1 | 1
16 | Legal and regulatory |  | Adequate insurance cover not in place |  |  |  |  | 1 | 1 | 1
17 | Legal and regulatory |  | Data Protection breach |  |  |  |  | 1 | 1 | 1
18 | Legal and regulatory |  | IT Security failure |  |  |  |  | 1 | 1 | 1
19 | Financial |  | Financial information – management accounts incorrect unapproved |  |  |  |  | 1 | 1 | 1
20 | Financial |  | Five year financial forecast not in place |  |  |  |  | 1 | 1 | 1
21 | Financial |  | Annual budget inaccurate |  |  |  |  | 1 | 1 | 1
22 | Financial |  | Too large/small financial reserves compared to published reserves policy |  |  |  |  | 1 | 1 | 1
23 | Financial |  | Fraud prevention control failure |  |  |  |  | 1 | 1 | 1
24 | Financial |  | Reliance on grants/income that could be lost |  |  |  |  | 1 | 1 | 1
25 | Financial |  | Investment management policies and performance |  |  |  |  | 1 | 1 | 1
26 | Financial |  | Ineffective management of property/asset maintenance/replacement |  |  |  |  | 1 | 1 | 1
27 | External |  | Adverse publicity/media coverage |  |  |  |  | 1 | 1 | 1
28 | External |  | Changing demographics of area leading to fewer or more young people and demand |  |  |  |  | 1 | 1 | 1
29 | External |  | Competition from other youth activity providers |  |  |  |  | 1 | 1 | 1
30 | External |  | Adults having less time to volunteer |  |  |  |  | 1 | 1 | 1
31 | [7 empty] | 1 | 1 | 1
32 | [7 empty] | 1 | 1 | 1
33 | [7 empty] | 1 | 1 | 1
34 | [7 empty] | 1 | 1 | 1
35 | [7 empty] | 1 | 1 | 1
36 | [7 empty] | 1 | 1 | 1
37 | [7 empty] | 1 | 1 | 1
38 | [7 empty] | 1 | 1 | 1
39 | [7 empty] | 1 | 1 | 1
40 | [7 empty] | 1 | 1 | 1
41 | [7 empty] | 1 | 1 | 1
42 | [7 empty] | 1 | 1 | 1
43 | [7 empty] | 1 | 1 | 1
44 | [7 empty] | 1 | 1 | 1
45 | [7 empty] | 1 | 1 | 1
46 | [7 empty] | 1 | 1 | 1
47 | [7 empty] | 1 | 1 | 1
48 | [7 empty] | 1 | 1 | 1
49 | [7 empty] | 1 | 1 | 1
50 | [7 empty] | 1 | 1 | 1
51 | [7 empty] | 1 | 1 | 1
52 | [7 empty] | 1 | 1 | 1
53 | [7 empty] | 1 | 1 | 1
54 | [7 empty] | 1 | 1 | 1
55 | [7 empty] | 1 | 1 | 1
56 | [7 empty] | 1 | 1 | 1
57 | [7 empty] | 1 | 1 | 1
58 | [7 empty] | 1 | 1 | 1
59 | [7 empty] | 1 | 1 | 1
60 | [7 empty] | 1 | 1 | 1
61 | [7 empty] | 1 | 1 | 1
62 | [7 empty] | 1 | 1 | 1
63 | [7 empty] | 1 | 1 | 1
64 | [7 empty] | 1 | 1 | 1
65 | [7 empty] | 1 | 1 | 1
66 | [7 empty] | 1 | 1 | 1
67 | [7 empty] | 1 | 1 | 1
68 | [7 empty] | 1 | 1 | 1
69 | [7 empty] | 1 | 1 | 1
70 | [7 empty] | 1 | 1 | 1

## How to Use this Template
Introduction
This risk register tracking template allows you to identify and track any risks to the day to day operation of yor group. It's critical to track risks, so they don't become issues that derail progress. This document is a living document, and should be frequently inspected and updated by your trustees. | Impact Score |  |  | Likelihood Score
| Descriptor | Score | Impact on service and reputation | Descriptor | Score | Example
Definition of Terms | Insignificant | 1 | no impact on our meetings / events | Remote | 1 | may only occur in exceptional circumstances
ID: The identification number of your risk. |  |  | no impact on reputation |  |  | (Rarely, if ever)
Description of Risk: Provide a brief description of your risk that anyone can understand. |  |  | complaint unlikely | Unlikely | 2 | expected to occur in a few circumstances
Impact: Outline the potential impact that risk can have on your project. |  |  | litigation risk remote |  |  | (Possible)
Risk Response: Describe what your reaction to the risk is, in order to quell it. | Minor | 2 | slight impact on our meeting / events | Possible | 3 | expected to occur in some circumstances
Risk Level: Define the priority of the risk; how likely it is to affect your group. |  |  | slight impact on reputation |  |  | (Likely)
Risk Owner: Define the team member or manager in charge of monitoring the risk. |  |  | complaint possible | Probable | 4 | expected to occur in many circumstances
Risk Action Owner: Define the team member who is responsible to the “risk owner” for developing and implementing the new controls that will, once operational, bring the risk within the trustee’s risk appetite. |  |  | litigation possible |  |  | (Very likely)
Likelihood Score: this is your assessment of the likehood of the risk happening (1 = low & 5 = high) | Moderate | 3 | some disruption to our meeting / events | Guaranteed | 5 | Will happen or is happening
Impact Score: this is your assessment of the impact the risk would have on your group (1 = low & 5 = high) |  |  | potential for adverse publicity - avoidable with careful handling |  |  | (Unavoidable / already occurring)
Overall Score: this is automaticlly worked out for you based on you likelihood and impact scores (1 = low & 10 = high) |  |  | complaint probable
Notes: Add any notes you may have for a better understanding of the risk. Update regularly. |  |  | litigation probable
| Major | 4 | our meeting / events disrupted
adverse publicity not avoidable (local media)
complaint probable
litigation probable
Sudden loss of funding
| Extreme | 5 | our meeting / events interrupted for
significant time
major adverse publicity not avoidable
(national media)
major litigation expected
resignation of senior management/leadership
resignation of executive committee
major premises related issue
loss of members confidence